## Sheet1
| 10월27일 | 10월28일 | 10월29일 | 10월30일 | 10월31일 | 11월1일 | 11월2일 | 11월3일 | 11월4일 | 11월5일 | 11월6일 | 11월7일 | 11월8일 | 11월9일 | 11월10일 | 11월11일 | 11월12일 | 11월13일 | 11월14일 | 11월15일 | 11월16일 | 11월17일 | 11월18일 | 11월19일 | 11월20일 | 11월21일 | 11월22일 | 11월23일 | 11월24일 | 11월25일 | 11월26일 | 11월27일 | 11월28일 | 11월29일 | 11월30일
작업예정 | Pushing, Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Skill, Ridding ,Status, State Component | Skill, Ridding, State Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Ridding, Inventory Component | Ridding, Inventory Component | Ridding, Inventory Component | Ridding, Inventory Component | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현
작업중 | 기본캐릭터 구조 (기본 조작 및 애니메이션) | PushingComponent (SphereComponent 상속) HP UI | WeaponComponent | PushingComponent 수정 | 아이템구조작성 | Citem | Citem Cequip | Citem CEquip CWeapon CDoAction (좌클릭, 우클릭 콤보 섞어 가능하게.) | CWeapon CDoAction StatusCompoent | CWeapon CDoAction StatusCompoent StateComponent | CWeapon CDoAction StatusCompoent StateComponent | CWeapon CDoAction Cequipment CEquipActor StatusCompoent StateComponent | CWeapon CDoAction CEquipment StatusCompoent StateComponent | CWeapon CDoAction CEquipment StatusCompoent | StatusCompoent InventoryComponent | StatusCompoent InventoryComponent | StatusCompoent InventoryComponent | StatusCompoent InventoryComponent | CSkill CSkill_Passvie CSkill_Active | CSkillComponent CSkill_Active_Slash CSlashProjectile | CSkillComponent CSkill_Active_Slash | CSkillComponent CSkill_Active_Slash 스킬 단축키 설정 구현 | CSkillComponent CSkill_Active_Slash CSkill_Active_Throw | CSkillComponent CSkill_Active_Throw | CSkillComponent CSkill_Active_Throw | CSkillComponent CSkill_Active_Throw CBoomerang_Thorw | CSkillComponent ItemSystem | CDropItem | InventoryComponent
작업완료 |  | 기본 캐릭터 구조 | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem Cequip | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem Cequip | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem Cequip | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem