## 작업일지
| 10월27일 | 10월28일 | 10월29일 | 10월30일 | 10월31일 | 11월1일 | 11월2일 | 11월3일 | 11월4일 | 11월5일 | 11월6일 | 11월7일 | 11월8일 | 11월9일 | 11월10일 | 11월11일 | 11월12일 | 11월13일 | 11월14일 | 11월15일 | 11월16일 | 11월17일 | 11월18일 | 11월19일 | 11월20일 | 11월21일 | 11월22일 | 11월23일 | 11월24일 | 11월25일 | 11월26일 | 11월27일 | 11월28일 | 11월29일 | 11월30일 | 12월01일 | 12월02일 | 12월03일 | 12월04일 | 12월05일 | 12월06일 | 12월07일 | 12월08일 | 12월09일 | 12월10일 | 12월11일 | 12월12일 | 12월13일 | 12월14일 | 12월15일 | 12월16일 | 12월17일 | 12월18일 | 12월19일 | 12월20일 | 12월21일 | 12월22일 | 12월23일 | 12월24일 | 12월25일 | 12월26일 | 12월27일 | 12월28일 | 12월29일 | 12월30일 | 12월31일
작업예정 | Pushing, Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Weapon, Skill, Ridding Component | Skill, Ridding ,Status, State Component | Skill, Ridding, State Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Skill, Ridding Component | Ridding, Inventory Component | Ridding, Inventory Component | Ridding, Inventory Component | Ridding, Inventory Component | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding, Inventory Component 스킬 단축키 설정 구현 | Ridding 스킬 단축키 설정 구현 | Ridding 스킬 단축키 설정 구현 | Ridding 스킬 단축키 설정 구현 | Ridding 스킬 단축키 설정 구현 | Ridding 스킬 단축키 설정 구현 | Ridding Navigation 스킬 단축키 설정 구현 | Ridding Navigation | Ridding Navigation SkillComponent QuickSlotComponent 기타 스킬 | Ridding Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation SkillComponent QuickSlotComponent 기타 스킬 |  |  | Navigation SkillComponent QuickSlotComponent 기타 스킬 | Navigation 기타 스킬 | Navigation 기타 스킬 | Navigation 기타 스킬 | Navigation 기타 스킬 | Navigation 기타 스킬 | Navigation 기타 스킬 |  | Navigation 기타 스킬 QuickSlotComponent QuickSlotWidget | Navigation 기타 스킬 QuickSlotComponent QuickSlotWidget | Navigation
작업중 | 기본캐릭터 구조 (기본 조작 및 애니메이션) | PushingComponent (SphereComponent 상속) HP UI | WeaponComponent | PushingComponent 수정 | 아이템구조작성 | Citem | Citem Cequip | Citem CEquip CWeapon CDoAction (좌클릭, 우클릭 콤보 섞어 가능하게.) | CWeapon CDoAction StatusCompoent | CWeapon CDoAction StatusCompoent StateComponent | CWeapon CDoAction StatusCompoent StateComponent | CWeapon CDoAction Cequipment CEquipActor StatusCompoent StateComponent | CWeapon CDoAction CEquipment StatusCompoent StateComponent | CWeapon CDoAction CEquipment StatusCompoent | StatusCompoent InventoryComponent | StatusCompoent InventoryComponent | StatusCompoent InventoryComponent | StatusCompoent InventoryComponent | CSkill CSkill_Passvie CSkill_Active | CSkillComponent CSkill_Active_Slash CSlashProjectile | CSkillComponent CSkill_Active_Slash | CSkillComponent CSkill_Active_Slash 스킬 단축키 설정 구현 | CSkillComponent CSkill_Active_Slash CSkill_Active_Throw | CSkillComponent CSkill_Active_Throw | CSkillComponent CSkill_Active_Throw | CSkillComponent CSkill_Active_Throw CBoomerang_Thorw | CSkillComponent ItemSystem | CDropItem | InventoryComponent | InventoryComponent InventoryWidget | InventoryComponent InventoryWidget | InventoryComponent InventoryWidget | InventoryComponent InventoryWidget | ConsumableItem | ConsumableItem Potion | HitWidget | HitWidget | SkillComponent QuickSlotComponent 기타 스킬 | 아이템구조 재정리 | 아이템구조 재정리 DataAsset 실험 | Ridding | Ridding | Ridding | Ridding | Ridding Jump Skill | Bow | Bow Bow_Skill | Bow Bow_Skill | Bow Bow_Skill | Bow |  |  | Bow | SkillComponent SkillTree_Widget QuickSlotComponent | SkillTree_Widget QuickSlotComponent | QuickSlotComponent | QuickSlotComponent QuickSlotWidget | QuickSlotComponent QuickSlotWidget | QuickSlotComponent QuickSlotWidget |  | Widget 구조 변경 | Widget 구조 변경 Widget TitleBar | 기타 스킬 QuickSlotComponent QuickSlotWidget
작업완료 |  | 기본 캐릭터 구조 | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem Cequip | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem Cequip | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem Cequip | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill |  |  | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget |  | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget | 기본 캐릭터 구조 PushingComponent (SphereComponent 상속) HP UI Citem CEquipActor CEquipActor_Dual StateComponent+BE5 CWeaponAsset CDoAction Cequipment StatusCompoent CSkill CSkill_Passive CSkill_Active CSlashProjectile CSkill_Active_Slash CSkill_Active_Throw CBoomerang_Thorw CDropItem InventoryComponent InventoryWidget HitWidget Ridding Jump Bow_Skill Bow SkillComponent SkillTree_Widget Widget 구조 변경 Widget TitleBar

## Sheet1
Navgation
SkillTree
Skill
Consumable |  | QuickSlot
Amor
Critical
Ridding
AI
PlayerUI
EquipWidget
장비창 https://www.youtube.com/watch?v=a9iho861SlY